## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Create account (Jareth) | Make view for creating an account | 0.5 | 0 | 0 | 0.5 | 0.5
Create account (Jareth) | Make model for creating an account | 1 | 0 | 1 | 1 | 1
Create account (Jareth) | Make viewmodel for creating an account | 1 | 0 | 0 | 0 | 1
Login (Jareth) | Make view for logging in | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Login (Jareth) | Make model for logging in | 1 | 0 | 1 | 1 | 1
Login (Jareth) | Make view model for logging in | 1 | 0 | 0 | 1 | 1
Make meal | Make model class for ingredient | 1
Make meal | Make model class for meal | 1
View planner (Kirya) | Make view for viewing planner | 0.5 | 0.5 | 0
View planner (Kirya) | Make model for the planner | 1.5 | 1.5 | 1.5
View planner (Kirya) | Make viewmodel for viewing planner | 1 | 1 | 1
Add meal to planner | Update planner UI to display meal information | 1.5
Generate grocery list | Make view for the grocery list | 0.5
Generate grocery list | Make model for the grocery list | 1
Generate grocery list | Make view model for the grocery list | 1
| Estimate Totals | 14 | 3.5 | 5 | 4 | 5
|  |  | 14 | 14 | 14 | 14