## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2
View Meal | Make meal serialization (Jareth) | 5 | 5 | 5
Maintaince | Fix Tests (Jareth) | 3 | 0 | 3
View Meal | Fix Persistence on Logout (Jareth) | 2 | 0 | 2
| Estimate Totals | 10 | 5 | 10
|  |  | 10 | 10