## Sheet1
Related User Story | Task Description | Initial Estimate | Hours spent
|  |  | Week 1 | Week 2 | Week 3 | Week 4
As a user I want to view planned meals so I can see what I have planned | Implement viewing planned meals | 3 | 5 | 0 | 0 | 0
As a user I want to generate a grocery list so that I can see what ingredients are necessary to make planned meals | Complete GroceryList | 2
As a user I want to have my planner information saved so I can access and use old information | Basic Server Setup | 3
As a user I want to be able to login so I can save my information | Login (Client) | 3
As a user I want to be able to login so I can save my information | Login (Server) | 3
As a user I want to be able to create an account so I can log in | Create Account (Client) | 3
As a user I want to be able to create an account so I can log in | Create Account (Server) | 3
As a user I want to make meal so I can add it to my planner | Make Meal (Client) | 3
As a user I want to make meal so I can add it to my planner | Make Meal (Server) | 3
As a user I want to see what meals I have planned | View Meal (Client) | 3
As a user I want to see what meals I have planned | View Meal (Server) | 3 | 0 | 2 | 0 | 0
| Estimate Totals | 32 | 5 | 2 | 0 | 0
|  |  | 32 | 32 | 32 | 32